## Sheet1
USER STORIES
SPRINT 1 | Date of submission : 21/02/2018
Priority | User story | Scheduling(in days) | Allotment of tasks
1 | As user I can sign up as a new user for github. | 2 | Akshay
2 | As user I can log into my account so that I can access my github account. | 3 | Akshay
3 | As user I can create new repository for my project so that I can do management of my project or files. | 3 | Dhruv
4 | As user I can clone projects so that I can download that projects into my locale system | 4 | Dhruv
5 | As user I can track my file or project so that I can see different changes made to that file or project whenever I want. | 5 | Parth
6 | As user I can search project so that I can clone or download that project. | 3 | Parth
SPRINT 2
1 | As user I can rate different people project so that it helps other people to identify the goodness of that project. |  | Akshay
2 | As user I can give star to any repository so that I can see all those stared repository in my profile |  | Akshay
3 | As user I can “Watch and Unwatch” any public repository so that I can always be notified about the changes where made to those repository. |  | Akshay
4 | As user I can create branch in my repository when I am working on different version of the repository at the same time so that It is easy to maintain Main repository |  | Parth
5 | As user I can add file to “.gitignore” folder so that I can add the exception for that file from tracking of git. |  | Dhruv
6 | As user I can see the history of commit so that I can see what and which and where the changes made. |  | Dhruv